## Sheet1
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In charge | Status | Actual | Updated | Update Details
1 | HOME PAGE_Show top bird course | Public | Customer | - Display the most trending bird course that was best rated by customer, the information includes: + Price tag + Course name + Suitable bird type + Course duration + Average rate reviewed by customers | FE: Võ Minh Thắng BE: Hoàng Kim Nam |  | iter1
2 | HOME PAGE_Show top workshop | Common | Customer | - Display the most trending bird course that was best rated by customer, the information includes: + Price tag + Workshop name + Short description + Date and time + Workshop location + Target audience | FE: Võ Hoàng Vũ BE: Trần Hoàng Đức |  | tier1
3 | HOME PAGE_Show top Online course | Common | Customer | - Display the most trending online course that was best rated by customer, the information includes: + Price tag + Course name + Course duration + Average rating viewed by the customers | FE: Võ Hoàng Vũ BE: Hoàng Kim Nam |  | Iteration3
4 | HOME PAGE_Show number of trainers | Public | Customer | - Display the list of trainers who are currently responsible for teaching Bird Training Center, a trainer information includes: + Trainer full name + Trainer role (profession) - A "View information" button helps customer access trainer's profile | FE: Võ Minh Thắng BE: Nguyễn Duy Tấn Hùng |  | Iteration3
5 | HOME PAGE_Show customer's feedback | Public | Customer | Display the customer's feedback about the center's services, that shows the following information + Customer's name + Customer comments | FE: Đỗ Đặng Phúc Anh BE: Nguyễn Duy Tấn Hùng |  | Iteration3
6 | LOGIN_forgot password | Customer | Customer | - Display the forgot password screen where customer have to input required information to retrieve their lost password + Email address - The system checks the email validation then send the OTP code to customer email and redirects user to the OTP code input - The system checks for code validation, if the code is matched, it will redirects customer to reset password screen where customer have to input required information: + New password + Confirm new password | FE: Võ Hoàng Vũ BE: Hoàng Kim Nam |  | Iteration1
7 | Register | Customer | Customer | - Display the registration screen for customer who does not have an account, the required information for account creation includes + First name + Last name + Phone number + Username + Password + Confirm password - A button for account creation if user inputted all the required information | FE: Võ Minh Thắng BE: Hoàng Kim Nam |  | Iteration2
8 | Web Blogs List _Show list of blogs | Customer | Customer | - Display a list of blog selection that includes + Blog image + Blog title + Date of publication + Author + Brief blog post content - A button at the end of each blog selection helps user to visit a detail of a blog | FE: Võ Minh Thắng BE: Trần Hoàng Đức |  | Iteration2
9 | Web Blogs List _Search blog | Public | Customer | - Allow user to search for related blog post that corresponds with their search result | FE: Võ Hoàng Vũ BE: Hoàng Kim Nam |  | Iteration1
10 | Web Blogs Details_Show blog detail | Public | Customer | - Display the content of the blog that includes + Date of publication + Author + Reading duration + Blog title + Blog conent (head, body, closing, images) - An interactive vote button for post voting - A selection of suggested of other blogs at the end of the blog | FE: Võ Hoàng Vũ BE: Hoàng Kim Nam |  | Iteration1
11 | Bird Course (Enrolled)_Show bird course enrolled | Public | Customer | - Display a list of booked bird courses. Each includes the following information: + Course name + Training duration + Bird's name + Bird type | FE: Võ Minh Thắng BE: Hoàng Kim Nam |  | Iteration1
12 | Private Consultation (Enrolled)_Show private consultation enrolled | Public | Customer | - Display a list of booked private consultations. Each includes the following information: + Consultation name + Trainer/Instructor name + Date + Time | FE: Võ Hoàng Vũ BE: Hoàng Kim Nam |  | Iteration1
13 | Workshop (Enrolled)_Show workshop enrolled | Public | Customer | - Display a list of enrolled workshops. Each includes the following information: + Workshop name + Workshop image + Workshop description + Starting date + Time + Location/Venue + Target audience - Display a search bar and a search button to search workshop by name - Display the total of workshops being displayed. | FE: Võ Minh Thắng BE: Hoàng Kim Nam |  | Iteration1
14 | Online Course (Enrolled)_Show online course enrolled | Public | Customer | - Display a list of enrolled online courses. Each includes the following information: + Course name + Course image + Course description + A button linked to the course's detail page - Display a search bar and a search button to search course by name - Display the total of workshops being displayed. | FE: Võ Hoàng Vũ BE: Hoàng Kim Nam |  | Iteration1
15 | Online Course (Enrolled)-Detail_Show certificate | Public | Customer | - Display a certificate containing the following information: + Customer's name + Course's name + Course skills + Date complete + Trainer's name | FE: Đỗ Đặng Phúc Anh BE: Hoàng Kim Nam |  | Iteration1
16 | Bird Course (Enrolled)-Detail_Show certificate | Customer | Customer | - Display a certificate containing the following information: + Customer's name + Course's name + Course skills + Date complete + Trainer's name | FE: Võ Hoàng Vũ BE: Hoàng Kim Nam |  | Iteration1
17 | Bird Course (Enrolled)_Show detail of bird course | Customer | Customer | - Display a bird course detail card, including the following information: + Course name + Course image + Bird type + Duration/Number of modules + Ratings - Display information about the topics, course, and duration | FE: Đỗ Đặng Phúc Anh BE: Trần Hoàng Đức |  | Iteration1
18 | Online Course (Enrolled)_Show detail of online course | Customer | Customer | - Display an online course detail card, including the following information: + Course name + Course image + Duration/Number of modules + Ratings - Display information about the topics, course, and duration - Display list of modules, each containing the following information: + Module name + Module summary + Module detail | FE: Võ Minh Thắng BE: Hoàng Kim Nam |  | Iteration3
19 | Private Consultation (Enrolled)_Show detail of private consultation | Common | Customer | - Display a form containing the following information: + Customer full name + Customer phone number + Customer address + Date & time request + Total price + Trainer requested + Customer's note | FE: Võ Hoàng Vũ BE: Nguyễn Duy Tấn Hùng |  | Iteration4
20 | Workshop (Enrolled)_Show detail of workshop | Public | Customer | - Display a workshop detail card, including the following information: + Workshop name + Trainer/Instructor name + Duration + Date + Time + Location/Venue + Target Audience + Workshop description | FE: Đỗ Đặng Phúc Anh BE: Trần Hoàng Đức |  | Iteration3
21 | Bird Course List _ Show list of bird course | Trainer | Customer | - Display a search bar and a search button to search course by name - Display 2 filters: filter by skill and filter by species - Display a list of enrolled bird courses. Each includes the following information: + Course name + Course image + Course price + Bird type + Duration/Number of modules + Ratings + A button linked to the bird course detail page | FE: Đỗ Đặng Phúc Anh BE: Nguyễn Duy Tấn Hùng |  | Iteration1
22 | Bird Course Detail _Form for enrolling course | Trainer | Customer | - Display form submission, including the following information: + Bird's name + Bird type + Bird image attachment + Payment method + Submit form button - Display payment details, including the following information: + Course name + Course price + Course image + Subtotal + Value-added tax + Total | FE: Võ Minh Thắng BE: Tràn Hoàng Đức |  | Iteration3
23 | Bird Course Detail _Show detail information of bird course | Admin | Customer | - Display a bird course detail card, including the following information: + Course name + Course image + Course price + Bird type + Duration/Number of modules + Ratings + A button linked to form for enrolling course - Display information about the topics, course, and duration | FE: Võ Hoàng Vũ BE: Hoàng Kim Nam |  | Iteration3
24 | Workshop List _ Show list of workshop | Admin | Customer | - Display a search bar and a search button to search workshop by name - Display filter by date - Display sorter: price (low to high, high to low), duration (long to short, short to long) - Display a list of workshops. Each includes the following information: + Workshop name + Workshop image + Workshop description + Workshop price + Starting date + Time + Location/Venue + Target Audience + Close registration date + A button linked to the workshop detail page | FE: Đỗ Đặng pHúc Anh BE: Nguyễn Duy Tấn Hùng |  | Iteration3
25 | Workshop Detail _ Show detail information of workshop | Staff | Customer | - Display a bird course detail card, including the following information: + Workshop name + Workshop image + Workshop description + Workshop price + Starting date + Time + Location/Venue + Target Audience + Close registration date | FE: Võ Minh Thắng BE: Trần Hoàng Đức |  | Iteration4
26 | Workshop Detail _ Payment | Staff | Customer | - Display a customer details by email. | FE: Võ Hoàng Vũ BE: Hoàng Kim Nam |  | Iteration4
27 | Online course list _ Show list of online course | Staff | Customer | - Display a search bar and a search button to search course by name - Display a list of enrolled online courses. Each includes the following information: + Course name + Course image + Course price + Duration/Number of modules + Ratings + A button linked to the online course detail page | FE: Đỗ Đặng pHúc Anh BE: Nguyễn Duy Tấn Hùng |  | Iteration4
28 | Online course detail _ Show detail information of online course | Staff | Customer | - Display a online course detail card, including the following information: + Course name + Course image + Course price + Duration/Number of modules + Ratings + A button linked to form for enrolling course - Display information about the topics, course, and duration | FE: Võ Minh Thắng BE: Trần Hoàng Đức |  | Iteration3
29 | Online course detail _ Payment | Staff | Customer | - Display a customer details by email. - Display a button "Continue with VNPAY" link to VNPAY payment section. - Display a online course detail card, including the following information: + Course name. + Online course price. + Subtotal of online course. + Value-added tax of online course. + Total price of online course. | FE: Võ Hoàng Vũ BE: Hoàng Kim Nam |  | Iteration2
30 | Private Consultation _ Show list of trainers | Staff | Customer | - Display a list of trainers with these informations including: + Trainer Name. + Achievement. + A button "Book now" link to "Select trainer" on Private Consultation Form section. | FE: Võ Minh Thắng BE: Trần Hoàng Đức |  | Iteration2
31 | Private Consultation _ Form | Staff | Customer | - Display a form including following informations: + Display buttons that link Center's social media plat-form: Facebook, Instagram, Youtube. + Display Center's informations including: email, phone. + Display a form that allow customer to fill in their email for website subscription. + Display a form including following information: * Customer's full name. * Customer's home address. * Customer's phone number. * Select trainer button that allow customer to choose who will have a private consultation with her/him. * Customer's request message. * Consultation option: online, offline. * Submit button allow customer to submit their form to staff | FE: Võ Minh Thắng BE: Nguyễn Duy Tấn Hùng |  | Iteration1
32 | Profile customer _ Update information | Staff | Customer | - Display a update form including following informations: + User Name. + Phone. + Email. + Home Address. | FE: Võ Minh Thắng BE: Nguyễn Duy Tấn Hùng |  | Iteration1
33 | Profile customer _ Change password | Staff | Customer | - Display a button "Change Password" links to Change password page that allow customer to change his/her password. | FE:Võ Hoàng Vũ BE: Nguyễn Duy Tấn Hùng |  | Iteration1
34 | About us | Common | Customer | - Display a banner of About Us's page. - Display a trainers display a trainers's image and their name. - Display "Why choose us" section. - Display 4 card of webpage result including: + Years of expetience. + Total birds trained. + Bird trainers. + Monthly training. | FE: Đỗ Đặng Phúc Anh BE: Trần Hoàng Đức |  | Iteration3
35 | Bird Course (CRUD) | Common | Staff | - Allow staffs to update content of course. This page will have a button (submit) for staff to complete updating. - Allow staffs to add new course by fill form. This form will include: thumbnail, title, date, author, details information about this course. - This page will have a button (submit) to complete creating and cancel to exit create a new course. | FE: Võ Minh Thắng BE: Hoàng Kim Nam |  | Iteration3
36 | Workshop (CRUD) | Staff | Staff | - Allow staffs to update content of workshop. This page will have a button (submit) for staff to complete updating. - Allow staffs to add new workshop by fill form. This form will include: title, date, author, details information about this workshop. - This page will have a button (submit) to complete creating and cancel to exit create a new workshop. | FE: Võ Hoàng Vũ BE: Nguyễn Duy Tấn Hùng |  | Iteration3
37 | Online course (CRUD) | Staff | Staff | - Allow staffs to update content of course. This page will have a button (submit) for staff to complete updating. - Allow staffs to add new course by fill form. This form will include: thumbnail, title, date, author, details information about this course. - This page will have a button (submit) to complete creating and cancel to exit create a new course. | FE: Đỗ Đặng Phúc Anh BE: Trần Hoàng Đức |  | Iteration4
38 | Order list (Staff) _ List completed | Staff | Staff | - Show list of invoice that customer book a course and they want to pay offline.This invoice will include : id form , username of customer, course , date , price and the right of card will have a button( Availbale/ Not Available) for staff to check the payment. | FE: Võ Minh Thắng BE: Tràn Hoàng Đức |  | Iteration1
39 | Account List (Admin) _ Show list of account | Trainer | Admin | - Show list of account . Each acount include: avatar , id , username, role .Admin will be redicted to Account List Page when they click to each card list . | FE: Đỗ Đặng Phúc Anh BE: Nguyễn Duy Tấn Hùng |  | Iteration1
40 | Account Detail (Admin) _ CRUD | Staff | Admin | - Show information for each account - Show information: id , username, password, gmail . - They can set role by choose dropdown-menu for each account (trainer, staff, customer). | FE: Võ Hoàng Vũ BE: Hoàng Kim Nam |  | Iteration4
42 | Web Course List (Trainer) _ Workshop _ in progress | Customer | Trainer | - Show course that are assigned, detail information of workshop: + Workshop name + Date and Time + Location + Duration + Assigned Participants + Status + Button to check "complete" When the workshop complete, trainer of this workshop will click 'complete' button. | FE: Võ Hoàng Vũ BE: Nguyễn Duy Tấn Hùng |  | Iteration1
43 | Web Course List (Trainer) _ Workshop _ complete | Customer | Trainer | - Show course that are completed, detail information of workshop: + Workshop name + Date and Time + Location + Duration + Assigned Participants + Status | FE: Võ Minh Thắng BE: Tràn Hoàng Đức |  | Iteration4
44 | Web Course List (Trainer) _ Bird Course _ in progress | Staff | Trainer | - Show course that are assigned, detail information of bird course: + Course Name + Start Date and Time + End Date and Time + Trainer + Enrolled Participants + Status + Button to tracking bird course | FE: Võ Hoàng Vũ BE: Hoàng Kim Nam |  | Iteration2
45 | Web Course List (Trainer) _ Bird Course _ complete | Staff | Trainer | - Show course that are assigned, detail information of bird course: + Course Name + Start Date and Time + End Date and Time + Trainer + Enrolled Participants + Status | FE: Võ Hoàng Vũ BE: Hoàng Kim Nam |  | Iteration2
46 | Web Course List (Trainer) _ Bird Course _ set status | Trainer | Trainer | - This screen will show detail of bird course which trainer is assigned. There are a function for trainer update status about course. There are 3 categories: "check-in; in-training; check-out" | FE: Võ Hoàng Vũ BE: Hoàng Kim Nam |  | Iteration1
47 | Web Course List (Trainer) _ Private Consultation _ in progress | Trainer | Trainer | - This screen show all the private consultation which trainer is assigned for. The screen displays: + The name of customer + Type of private consultation (online / offline) + Date and Time of private consultation + Button to view detail information of the private consultation | FE: Võ Hoàng Vũ BE: Hoàng Kim Nam |  | Iteration1
48 | Web Course List (Trainer) _ Private Consultation _ complete | Trainer | Trainer | - This screen show all the private consultation which trainer completed. The screen displays: + The complete date + Type of private consultation (online / offline) + Date and Time complete consultation. | FE: Võ Hoàng Vũ BE: Hoàng Kim Nam |  | Iteration1
49 | Web Course List (Trainer) _ Private Consultation _ detail | Trainer | Trainer | This screen show details of private consultation which contain following detail information : + At the top form detail , conatin (Consultation id, date submit , type of consultation + Information of guest : (fullName,gmail ,address, contact ) + Request information(Title of course , trainer, date start , time start , note of customer ) . And [ Complete ] button to chanmge the status of this consultation to be completed. | FE: Võ Hoàng Vũ BE: Hoàng Kim Nam |  | Iteration1
50 | Web Course List (Trainer) _ Private Consultation _ payment | Customer | Trainer | This function only show when Trainer click [ Complete ] button . This screen contain + A input text form for Trainer can input the Time for consultaiton + The a box to get the result + The [Complete] button to ensure payment processing is completed | FE: Võ Hoàng Vũ BE: Tràn Hoàng Đức |  | Iteration1
51 | Blog (Trainer) _ CRUD (***) | Staff | Staff | This creen contain four function with the blog features (create , update , delete ,read): + The read function: Trainer can view a list blogs , each blogs contain : title , date created , author content , thumbnail , image , preferences , brief-info . + The update function : Trainer can update information of Blog by click [edit] form form options in trainer view which contain information : (title , date created , author content , thumbnail , image , preferences , brief-info . ) + The delete function: This screen include [ delete] button in the sreen trainer . + The create function This screen include [ Create ] button in the screen trainer . When trainer click in this button will some a form for trainer can edit : title , date created , author content , thumbnail , image , preferences , brief-info . | FE: Võ Hoàng Vũ BE: Tràn Hoàng Đức |  | iteration 1
52 | Set trainer for each consultation (Staff) | Staff | Staff | This function show a button set trainer for staff can set a trainer for course + When click a set trainer , it will show a list of trainer which are not in task consultation . Each trainer contain some information: Images , Full Name, SKill , Achievement . + Ecah trainer has a select button for staff can click and set trainer . | FE: Võ Hoàng Vũ BE: Tràn Hoàng Đức |  | iteration 1
53 | Pending Order Consultation_ List | Staff | Staff | This screen show a list of pending order consultation: Each order consultation contain : ID , Titile , Name of Customer ,Appointment Date request ( start date and start time) , Trainer Request , Submitted date , Type and Button [View Detail ] . | FE: Võ Hoàng Vũ BE: Tràn Hoàng Đức |  | iteration 1
54 | Pending Order Consultation _ Detail | Staff | Staff | This screen show a detail of pending order consultation: Each order consultation contain : + At the top form detail , conatin (Consultation id, date submit , type of consultation + Information of guest : (fullName,gmail ,address, contact ) + Request information(Title of course , trainer, date start , time start , note of customer ) . And [ Complete ] button to chanmge the status of this consultation to be completed. | FE: Võ Hoàng Vũ BE: Tràn Hoàng Đức |  | iteration 1
55 | Processing Order Consultation _ List | Trainer | Staff | This screen show a list of processing order consultation: Each order consultation contain : ID , Titile , Name of Customer ,Appointment Date request ( start date and start time) , Trainer Request , Submitted date , Type and Button [View Detail ] . | FE: Võ Hoàng Vũ BE: Tràn Hoàng Đức |  | iteration 1
56 | Processing Order Consultation _ Detail | Trainer | Trainer | This screen show a detail of processing order consultation: Each order consultation contain : + At the top form detail , conatin (Consultation id, date submit , type of consultation + Information of guest : (fullName,gmail ,address, contact ) + Request information(Title of course , trainer, date start , time start , note of customer ) | FE: Võ Hoàng Vũ BE: Tràn Hoàng Đức |  | iteration 1
57 | Complete Order Consultation _ List | Customer | Customer | This screen show a list of completed order consultation: Each order consultation contain : ID , Titile , Name of Customer ,Appointment Date request ( start date and start time) , Trainer Request , Submitted date , Type and Button [View Detail ] . | FE: Võ Hoàng Vũ BE: Hoàng Kim Nam |  | iteration 1
58 | Complete Order Consultation_ Detail | Customer | Customer | "This screen show a detail of completed order consultation: Each order consultation contain : + At the top form detail , conatin (Consultation id, date submit , type of consultation + Information of guest : (fullName,gmail ,address, contact ) + Request information(Title of course , trainer, date start , time start , note of customer ) . And [ Complete ] button to chanmge the status of this consultation to be history. " | FE: Võ Hoàng Vũ BE: Hoàng Kim Nam |  | iteration 1
59 | Pending order bird course _ Detail | Staff | Staff | This page displays information about booking that is pending with following attribute: Customer name, Bird name, Bird type, Course name, course price, preferred date, create date. This page allows staff to set a trainer to a booking. | FE: Võ Hoàng Vũ BE: Tràn Hoàng Đức |  | iteration 1
60 | Processing Order Bird Course _ List | Staff | Staff | This page displays a list of bookings that is processing (has status: approve, checkin, in-training) | FE: Võ Hoàng Vũ BE: Tràn Hoàng Đức |  | iteration 1
61 | Processing Order Bird Course _ Detail | Staff | Staff | This page displays information about bookings that is processing with following attribute: Customer name, Bird name, Bird type, Course name, status, create date, start_date, end_date. | FE: Võ Hoàng Vũ BE: Tràn Hoàng Đức |  | iteration 1
62 | Complete Order Bird Course _ List | Staff | Staff | This page displays a list of bookings that is done(has status: checkout) | FE: Võ Hoàng Vũ BE: Tràn Hoàng Đức |  | iteration 1
63 | Complete Order Bird Course_ Detail | Staff | Staff | This page displays information about bookings that is processing with following attribute: Customer name, Bird name, Bird type, Course name, status, create date, start_date, end_date, checkout_date | FE: Võ Hoàng Vũ BE: Tràn Hoàng Đức |  | iteration 1
64 | Checkout Bird Course_ List | Staff | Staff | This page display a list of bookings that has been completed (has status: completed) | FE: Võ Hoàng Vũ BE: Tràn Hoàng Đức |  | iteration 1
65 | Checkout Bird Course_ Detail | Staff | Staff | This page display infomation about bookings that has been completed with following attribute: | FE: Võ Hoàng Vũ BE: Tràn Hoàng Đức |  | iteration 1
66 | Dashboard _ View Revenue | Staff | Staff | This page display a chart illustrating the revenue of the center in the recent 6 months. | FE: Võ Hoàng Vũ BE: Tràn Hoàng Đức |  | iteration 3
67 | Dashboard _ Top 3 courses of each service | Staff | Staff | This page display 9 courses that have the most customer enrolled, 3 for each services | FE:Võ Hoàng Vũ BE: Nguyễn Duy Tấn Hùng |  | iteration 3
68 | Dashboard _ Top trainers of center | Staff | Staff | This page display 3 trainers that are most engaged in center's activities | FE:Võ Hoàng Vũ BE: Nguyễn Duy Tấn Hùng |  | iteration 3
69 | Dashboard _ View feedback and rating | Staff | Staff | This page display feedbacks and rating of each course. | FE:Võ Hoàng Vũ BE: Nguyễn Duy Tấn Hùng |  | iteration 3